## Slide 1: SUNY Fredonia Summer 2014 Projects

## Slide 2: Agenda
Academic / Administration Projects
Residence Hall Projects
Site Work
Minor Critical Maintenance Projects
Notable Construction Impact to Campus
Project Recap
Question and Answers

## Slide 3: Academic / Administration Projects
Science Center
RAC Addition & Renovation
Mason Hall
McEwen Hall
Fenton Hall
Thompson Hall
Steele Hall
Science Center [$60M]
Rockefeller Arts Center Addition and Renovation [$36M]
Rehab/Upgrade Elevators Various Buildings [$1.5M]
Maytum Hall
Houghton Hall Rehab [$33 M] (In Design)
Houghton Hall

## Slide 4: Residence Hall Projects
Townhouse ▪
Disney Hall
Igoe Hall
Grissom Hall
Kasling Hall
Nixon Hall
Chautauqua Hall
Hendrix Hall
Townhouse [$30M]
Disney Hall Lobby Upgrade [$550K]
Andrews Complex Window Replacement – IV Phases [$6.1M ]: Phase I – Igoe Hall [$1.5 M]
Interior Lighting and Occupancy Sensors – Grissom Hall / Kasling Hall [$150K]
Cleaning Limestone Window Sills – Chautauqua Hall / Nixon Hall [$9.8K]
ADA Signage – Hendrix Hall [$25K]
Interior Painting – Various Locations [$85K]
Student Rooms, Corridors
and Doors/Frames

## Slide 5: Site Work
Milling and Paving at Old Main Drive [Extending from Alumni Hall to LoGrasso Hall
Ring Road (Adjacent to Parking Lots 9A/9D) [$175K]
Parking Lot and Roadway (Crosswalks) Striping [$25K]
Old Main Drive
Ring Road
Parking Lot and Roadway Striping at Various Locations

## Slide 6: Minor Critical Maintenance Projects
Maytum Hall Mechanical Room Concrete Repair [$98K]
LoGrasso Hall Boiler [$30K]
Mason Recital Hall Reheat Boiler/Humidifier [$59K]
Natatorium Floor Repair [$33K]
RAC Generator Exhaust Fan [$20K]
Jewett Hall 101 Lighting [$35K]
Carnahan Jackson Center VAV Controller Replacement [$35K]
Thompson Hall Cooling Fan/Air Handling Unit Reheat Piping [$59K]
University Commons Ventilation Improvements [$18K]
Maytum Hall Mechanical Room
Concrete Repair
Thompson Hall Cooling Fan/AHU
Reheat Piping
Mason Recital Hall
Reheat Boiler/Humidifier
Jewett Hall 101 Lighting
University Commons
Ventilation Improvements
Natatorium Floor Repair
Carnahan Jackson Center VAV
Controller Replacement
RAC Generator Exhaust Fan
LoGrasso Hall Boiler

## Slide 7: Notable Construction Impact to Campus
Rockefeller Arts Addition and Renovation
  Installation of site access road starting May 5, 2014 completed May 26, 2014
  Varsity Drive through traffic closed starting May 26, 2014
  Installation of site security fence and construction trailers
  Addition foundation and superstructure
  Existing building interior renovations

## Slide 8: Rockefeller Arts Center Addition and Renovation
Ring Road
Lot 9A
Park Drive
Tennis Courts
Steele Hall
RAC
Mason Hall
Dods Hall
Varsity Drive
Varsity Drive
Parking Lot 27
Parking Lot 11
Natatorium
New Road
Project Limit Line
RAC Addition
Note: New Road is Bid Alt No. 3

## Slide 9: Notable Construction Impact to Campus
Rehab/Upgrade Elevators Various Buildings
Below is the proposed schedule to start and complete the work on certain elevators
during certain periods of time.
  Summer (May thru August)2014
    Fenton Hall –Complete replacement: There is a possibility that work could spill into the Christmas Break
    Mason Hall Addition – Installation of new lift
    Thompson Hall – Complete replacement of Elevator 1 (freight elev. located at south end of bldg.)
  Christmas Break 2014 - 2015
    Fenton Hall – Remaining work from summer 2014
    Maytum Hall – Elevator 1 & 2: Rope gripper replacement
    McEwen Hall – Elevator door replacement
  Summer (May thru August)2015
    Mason Hall Addition – Complete replacement
    Thompson Hall – Complete replacement of Elevator 2 (small passenger elev. located at north end of bldg.)

## Slide 10: Notable Construction Impact to Campus
Townhouse Project (possible impact)
  Landscape work within the complex and along Ring Road
Milling & Paving - Old Main Drive & Ring Road
    Old Main Drive: Start May 19th Complete Mid June
    Ring Road (adjacent to lot 9A/9D):
    Start May 19th Complete end of May (pending completion of campus bus stop and crosswalk work at Townhouse Commons Building)
  Crosswalk and Parking Lot Striping
    Work to be Performed in May and August

## Slide 11: Project Recap
Academic /Administration: [ $130.5M ]
  Science Center
  Rockefeller Arts Center Addition and Renovation
  Rehab/Upgrade Elevators Various Buildings
  Houghton Hall Rehab – Design Phase
Residence Hall: [ $32.3M ]
  Townhouse
  Disney Hall Lobby Upgrade
  Andrews Complex Window Replacement Phase One: Igoe Hall
  Interior Lighting and Occupancy Sensors – Grissom Hall /Kasling Hall
  Cleaning Limestone Window Sills – Chautauqua Hall / Nixon Hall
  ADA Signage – Hendrix Hall
  Interior Painting – Various Locations
Site Work: [ $200K ]
  Mill and Paving – Old Main Drive (Alumni to Largesse) / Ring Road (adjacent to lot 9A/9D)
  Parking Lot and Roadway Striping
MCM Projects: [ $387K ]
  Maytum Hall Mechanical Room Concrete [ $98K ]
  Mason Hall Recital Hall Reheat Boiler / Humidifier [ $59K ]
  Rockefeller Arts Center Generator Exhaust Fan [$20K ]
  Natatorium Concrete Floor Repair [ $33K ]
  LoGrasso Hall Boiler [ $30K ]
  Jewett Hall 101 lighting [ $35K ]
  Carnahan Jackson Center VAV Controller Replacement [ $35K ]
  Thompson Hall Cooling Fan / Air Handling Unit Reheat Piping [ $59K ]
  University Commons Ventilation Improvements[ $18K ]